# Volume 4

Council Delivery Plan 2010/2014

What the Council will do in 2010/11

This is North West Leicestershire District Council’s Delivery Plan for 2010 – 2014.  The delivery plan highlights what has been achieved in 2009/10 and what the Council aims to achieve during the next three years. The plan is in 4 volumes:

Volume 1:	Introduction, performance highlights and way forward, including a summary of volumes 2, 3 and 4.

Volume 2:	Our strategic direction and Future Plans

Volume 3:	Our Performance – a journey of improvement

Volume 4:	What the Council will do in 2010/11

# Our Plans

In order to ensure that we continue our journey of improvement and have clarity of focus each service produces a SMART plan that details their key actions over the forthcoming year.  The actions for the year are broken down into quarters in order for us to be able to monitor and manage our performance.

Actions that directly contribute to our outcomes from these plans form our core Council Delivery Plan and are seen as essential for us to achieve if we are going to achieve our ambitions and deliver against our priorities.  Complementing these actions are a set of indicators with targets that are formed from National Indicators and Local agreed indicators – whether we achieve the targets set against these indicators will tell us whether the “business” we are doing is delivering the required outcomes and providing excellent services and will inform the “score” we achieve as an authority within the Comprehensive Area Assessment (CAA).

In some areas because changes will take place over a period of time and not be measurable in a quarter, proxy indicators will be used.  These are indicators that suggest the likely progress, whilst not measuring that actual outcome.

Section One:	 Outcomes and their Measures

Each Priority has a number of outcomes that help explain what it means. In order for the Council and its customers to be able to tell whether it has achieved these outcomes, measures and targets have been assigned to each Priority: how the authority performs against these targets will be published at the end of the year.  Additionally, to assess our progress during the year, the Lead Officer will be asked to provide a status (red, amber, green) each quarter with a commentary on how the key actions supporting these outcomes are performing.

Section Two: 	Actions and their Measures

Each Outcome has a number of actions against it to make it happen – in order to measure whether these have taken place each action will have a measure that will monitored either quarterly or annually.  Where a measure is measured annually the Lead Officer will be asked to provide a status (red, amber, green) each quarter with a commentary on how the tasks supporting these actions are performing.

Section Three: 	Actions and their Tasks

Each action has a series of tasks/milestones; these will be monitored on a quarterly basis and feed into the commentary that identifies progress against actions.  If no task is due to take place in the quarter N/A will be shown.

Section Four:	Actions and their Risks

The risks identified against each action have been assessed and will form part of the corporate risk register and monitored on quarterly basis by Cabinet.

Section One:	 Outcomes and their Measures

PRIORITY: PRIDE IN OUR COMMUNITY

| Outcomes | Evidenced by – (Measure) | Lead Officer | Actual 2008/2009 | Estimate Year End 2009/2010 | Target 2010/11 |
| --- | --- | --- | --- | --- | --- |
| Children will have more places to go and things to do. | NI 21 Dealing with Local concerns about anti social behaviour and crime issues by the local Council and Police (Place Survey) | Director of Communities | 25% | 22% | 33% |
| Crime will be reduced as well as the fear of crime. |  |  |  |  |  |
| People will have decent, affordable homes to live in. | NI 155 Number of affordable homes delivered gross | Housing Futures Manager | 18 | 98 | 84 |
|  | NI 158 % of non decent homes | Head of Housing | 39% | 45% | 48% |
|  | NI 160 Local Authority Tenants’ satisfaction with Land Lord Services | Head of Housing | 75% | 75% | 77% |
| Peoplces overall health and well being will improve | NI119 Self reported measure of peoples overall health and well being. | Head of Culture and Leisure | 75.2 | N/A | TBC |
| Our older people can continue to live independently | NI 138 Satisfaction of people 65 and over with both home and neighbourhood | Head of Housing |  |  |  |
|  | NI 142 % of vulnerable people who are supported to maintain independent living | Head of Housing | 98.4% | 98.5% | 98.6% |

Section One:	 Outcomes and their Measures

PRIORITY: GREEN FOOTPRINTS

| Outcomes | Evidenced by (Measure) | Lead Officer | Actual 2008/2009 | Estimate Year End 2009/2010 | Target 2010/11 |
| --- | --- | --- | --- | --- | --- |
| The area’s carbon footprint will be reduced | NI 185 CO2 Reduction from Local Authority operations | Head of Place Shaping | N/A | TBC | 4% |
|  | Volume of CO2 not emitted in the District as a result of Green Footprints initiatives. | Head of Place Shaping | N/A | N/A | 5 tonnes |
| The amount of waste that goes to landfill is reduced | NI 192 Percentage of household waste sent for reuse, recycling and composting | Head of Street Management | 43.35% | 44.3% | 45% |

RIORITY: 	GREEN FOOTPRINTS

PRIORITY:	COALVILLES CHANGING

| Outcomes | Evidenced by (Measure) | Lead Officer | Actual 2008/2009 | Estimate Year End 2009/2010 | Target 2010/11 |
| --- | --- | --- | --- | --- | --- |
| The physical appearance of Coalville Town Centre is improved | More people satisfied with Coalville Town Centre (survey responses) | Director of Environment | N/A | TBC on completion of Place survey | An improved % on 2009/10 |
| The market will be improved and relocated. | More people perceive positive change has occurred in Coalville Town Centre over the past 5 years (survey responses) | Director of Environment | N/A | TBC on completion of Place survey | An improved % on 2009/10 |
| Economic development of town centre businesses is supported | Business Improvement District (BID) ballot held | Head of Place Shaping | No | No | Yes |
|  | Town Centre Partnership membership increases | Head of Place Shaping | 32 | 29 | 32 |
| Increased footfall of visitors to Coalville Town Centre | Increase in attendees for the Christmas light switch-on | Head of Place Shaping | 3500 | 5500 | 6000 |

Section One:	 Outcomes and their Measures

PRIORITY:	VALUE FOR MONEY

| Outcomes | Evidenced by (Measure) | Lead Officer | Actual 2008/2009 | Estimate Year End 2009/2010 | Target 2010/11 |
| --- | --- | --- | --- | --- | --- |
| Improved communications with communities, citizens and customers. | NI4 % of people who feel they can influence decisions in their locality | Head of Neighbourhoods &Communities | 24.8% | 25.05% | 26% |
| Improvements in the overall satisfaction with the area and sense of belonging. | NI 2 % of people who feel that they belong to their neighbourhood | Head of Neighbourhoods &Communities | 59.9% | 60% | 62% |
|  | NI 5 Overall general satisfaction with local area | Head of Neighbourhoods &Communities | 80.3% | 80.8% | 82% |
| Performance of the authority will go up, whilst costs will remain the same or go down. | NI 179 Value for Money | Head of finance | £691,008 | £603,099 | £666,521 |
| Residents’ issues will be responded to quicker and in a transparent and fair manner. | Reduction in levels of complaints to the Council | Customer Services Manager |  |  |  |

Section Two:	 Actions and their Measures

PRIORITY: PRIDE IN OUR COMMUNITY

| Outcomes | Action | Measure | Lead Officer | Actual 2008/2009 | Estimate Year End 2009/2010 | Target 2010/2011 |
| --- | --- | --- | --- | --- | --- | --- |
| Children will have more places to go and things to do. | Develop places, spaces and activities for Children & Young People | More community venues, sports facilities and play areas | Head of Leisure & Culture | N/A | N/A | 6 |
| Crime will be reduced as well as the fear of crime. | Work with partners to improve levels of public confidence | CRAVE Survey data, British Crime Survey data public confidence measures | Head of Neighbourhood and Communities | 43% | 47% | 55% |
|  | To make local communities safer by delivering the key objectives in the community Safety Strategy and reducing overall crime by 5% by March 2012 | Total recorded crime figures and the Crime Dashboard per crime category | Head of Neighbourhood and Communities | 100% achieved | 100% achieved | 100% achieved |
| People will have decent, affordable homes to live in. | Maximise delivery of affordable housing through partnership working | More affordable homes to meet identified housing needs | Housing Futures Manager | 18 | 98 | 84 |
|  | To Develop a Planning Strategy for the District | Planning Strategy developed to agreed timescales | Head of Place Shaping | N/A | N/A | Yes – Strategy approved |
|  | Implement the outcome of the High Investment Needs Properties Review completed in 2009/10, | NA | Head of Housing | N/A | N/A | N/A |
|  | Deliver Housing Planned Investment Programme 2010-11 | NI 158 % of non decent council homes | Head of Housing | 39% | 45% | 48% |
|  | Improve standards in the private rented housing sector | Private rented sector inspection programme completed | Head of Environmental Health | n/a | n/a | 90% |
|  | Increase the number of decent homes for vulnerable people in the private sector | Number of additional decent homes in private sector | Head of Environmental Health | N/A | 250 | 250 |
| Peoples overall health and well being will improve | Increase 16+ Physical Activity uptake | Total number of Active Together Physical Activity opportunities Total number of attendances at Active Together Physical Activity sessions | Head of Leisure & Culture | N/A | N/A | N/A |
| Our older people can continue to live independelty . | Significantly improve performance in the delivery of Disabled Facilities Grants and Aids and Adaptations | Increase in customer satisfaction for Disabled facilities Grants and Aids and Adaptations customers | Head of Housing & Head of Environmental Health | NA | 76% | TBC |
|  | Complete preparations for retendering of the Older Persons Service (Supporting People) funded services. | NI42 % of vulnerable people who are supported to maintain independent living | Head of Housing | 98.4% | 98.5% | 98.6% |

Section Two:	 Actions and their Measures

PRIORITY: GREEN FOOTPRINTS

| Outcomes | Action | Measure | Lead Officer | Actual 2008/2009 | Estimate Year End 2009/2010 | Target 2010/11 |
| --- | --- | --- | --- | --- | --- | --- |
| The area’s carbon footprint will be reduced | To establish the Green Footprints Community Network - a district wide network bringing together existing community groups, parish councils, elected members and individuals who are interested in green initiatives. | Number of community groups engaged in Green Footprints Community Network | Head of Place Shaping | N/A | N/A | 5 |
|  |  | Volume of CO2 not emitted in the District as a result of Green Footprints initiatives. | Head of Place Shaping | N/A | N/A | 5 tonnes |
| There will be an increase in the percentage of waste recycled | To prepare and implement a programme of targeted action to increase participation in the Council’s recycling collection schemes in areas where recycling performance is poor. | To be confirmed | Head of Street Management | 43.35% | 44.3% | 45% |
| There will be an improvement in the energy efficiency of buildings | To publicly launch the ‘ourplace’ design initiative and associated strategies | The majority of new housing schemes (of ten units or more) approved in 2010/11 are good or very good as assessed against the Building For Life criteria | Head of Place Shaping | N/A | 25% | 51% |

Section Two:	 Actions and their Measures

PRIORITY:	COALVILLES CHANGING

| Outcomes | Action | Measure | Lead Officer | Actual 2008/2009 | Estimate Year End 2009/2010 | Target 2010/11 |
| --- | --- | --- | --- | --- | --- | --- |
| The physical appearance of Coalville Town Centre is improved | To make improvements to Marlborough Square | Improvement works commenced before year-end | Coalville’s Changing Programme Manager | No | No | Yes |
| Economic development of town centre businesses is supported | Use the Council's assets effectively to deliver a more efficient Council and to contribute to Coalville Regeneration | Formal decision and progress on development of new Council offices/partnership hub | Coalville’s Changing Programme Manager | No | No | Yes |
|  | Engage Coalville businesses in setting up a Business Improvement District | BID ballot held | Head of Place Shaping | No | No | Yes |
|  | Support new Town Centre developments | Outstanding planning applications are taken through the appropriate legal route to determination | Head of Place Shaping | No | Yes | Yes |
| Increased footfall of visitors to Coalville Town Centre | Undertake a programme of Town Centre events to attracts visitors and support local businesses | Events undertaken as planned and on budget | Head of Place Shaping | Yes | Yes | Yes |

Section Two:	 Actions and their Measures

PRIORITY:	VALUE FOR MONEY

| Outcomes | Action | Measure | Lead Officer | Actual 2008/2009 | Estimate Year End 2009/2010 | Target 2010/11 |
| --- | --- | --- | --- | --- | --- | --- |
| Improved communications with communities, citizens and customers. | To implement Area Working across the District | Area Working project agreed and delivered to timescales | Head of Place Shaping | N/A | N/A | Yes – plan delivered |
|  | To improve the availability of performance information to customers and communities | Evidence of use by communities and customers | Head of Service Transformation |  |  |  |
| Improvements in the overall satisfaction with the area and sense of belonging. | To implement Area Working across the District | Area Working project agreed and delivered to timescales | Head of Place Shaping | N/A | N/A | Yes – plan delivered |
|  | To undertake targeted cleansing operations to improve the cleanliness of areas scoring poorly in the 4 monthly inspections | NI 195a Improved Street and environmental cleanliness (litter) NI 195b Improved Street and environmental cleanliness (detritus) | Head of Street Management | 5% 15% | 6% 14% | 6% 14% |
| Performance of the authority will go up, whilst costs will remain the same or go down. | Deliver procurement savings within the Housing Planned Improvement Savings | Identify Savings of £200,000 of cash for reinvestment into the HRA | Head of Service Transformation | £800,000 | £800,000 | £200,000 |
|  | Using the category lists to aggregate spend and there by improve value for money through combined spending | Reduction in current prices paid against prices achieved for the appropriate quality | Head of Service Transformation | N/A | N/A | 5% |
|  | Project Management and Support of High Risk Projects | % of project RAG status's that are green | Head of Service Transformation | N/A | 80% | 90% |
|  |  | Deliver % of Savings as identified within the VFM Programme | Head of Service Transformation | N/A | N/A | 90% |
| Residents’ issues will be responded to quicker and in a transparent and fair manner. | Developing a comprehensive plan to improving the Councils performance against the equalities framework and as such delivering services that meet customers needs | Positive outcome from external peer review | Head of Service Transformation | N/A | N/A | Achieving Level |

Section Three: 	Actions and their Tasks

PRIORITY: PRIDE IN OUR COMMUNITY

| Action | Lead Officer | Q1 Task | Q2 Task | Q3 Task | Q4 Task |
| --- | --- | --- | --- | --- | --- |
| To Develop a Planning Strategy for the District | Head of Place Shaping | Evidence Collected | Evidence collected and Strategy being drafted | Strategy approved by Council | No Quarterly Action |
| Develop places, spaces and activities for Children & Young People | Head of Leisure & Culture | Deliver Battle of the Bands and Picnic in the Park Youth Zone with targeted group of young people. | To ensure a co-ordinated and comprehensive summer holiday activity programme is delivered including playschemes, leisure centres and Positive Activity partners. | Facilitate round 3 play builder bids and work with Ellistown PC and young person action group in Ellistown for development of St Christopher’s play area for 13 yr+ provision | Promote and support the potential new Youth Club developments at Whitwick, Ashby Woulds and Measham. |
| Work with partners to improve levels of public confidence | Head of Neighbourhood and Communities | Work with County partners to agree ASB service standards | Publicise new ASB standards and ensure positive outcomes are widely communicated through communications group and through ASB Road show | ASB Roadshow to raise profile and perceptions | Analysis of CRAVE and Place Shaping data to identify trends and hotspots to inform future focus and actions |
| To make local communities safer by delivering the key objectives in the community Safety Strategy and reducing overall crime by 5% by March 2012 | Head of Neighbourhood and Communities | Tracking overall crime reduction rates and monitoring delivery of the four priorities identified in the 09-10 Community Safety Strategy refresh to ensure any necessary corrective action is taken to address underperformance | Tracking overall crime reduction rates and monitoring delivery of the four priorities identified in the Community Safety Strategy refresh to ensure any necessary corrective action is taken to address underperformance | Tracking overall crime reduction rates and monitoring delivery of the four priorities identified in the Community Safety Strategy refresh to ensure any necessary corrective action is taken to address underperformance. Annual priorities are refreshed. | Tracking overall crime reduction rates and monitoring delivery of the four priorities identified in the Community Safety Strategy refresh to ensure any necessary corrective action is taken to address underperformance. Strategy refresh document is published |
| Increase 16+ Physical Activity uptake | Head of Culture and Leisure | To deliver the first NWL Sport Relief Mile fun run and consider developing a triathlon series of Fun Runs, Fun Cycles and Fun Swims events to develop interest for beginners | Promote and deliver the Summer/Autumn Active NWL Together programme of sport and physical activities utilising new media channels such as facebook, text, and e-blasts. | Trial an incentive scheme to engage and encourage residents not achieving 3x30mins of physical activity to access discounted leisure centre provision and physical activity sessions. | To deliver the New Year, New You Active NWL promotional campaign. |
| Maximise delivery of affordable housing through partnership working | Housing Futures Manager | Seek off-site commuted sums on appropriate sites in lieu of on-site provision to create a future enabling fund, ring-fenced to support affordable housing provision | Contribute to the development of the new Affordable Housing Supplementary Planning Document | Explore possibility of private sector landlords letting properties at sub-market rents | Identify housing need in rural areas of the district through a mix of surveys conducted by the Rural Housing Enabler and Midlands Rural Housing and through consultation events |
| Implement the outcome of the High Investment Needs Properties Review completed in 2009/10, | Head of Housing | Implement outcome of detailed review of governance and contract procedure rule requirements for high cost voids Develop detailed communications plan to implement outcome of detailed review of low demand properties. | Commence communications with residents in low demand properties | Evaluate outcome of pilot study and report to staff, T&LCF, CLT, Scrutiny committee for dealing with high cost void properties | Report outcome of pilot study to Cabinet to establish ongoing policy for dealing with high cost void properties |
| Deliver Housing Planned Investment Programme 2010-11 | Head of Housing | Preferred procurement route determined for all works, and programme contents agreed | Completion of all contractors selection Contractors commenced works | 25%+ completion of all budgeted works | 80%+ completion of all budgeted works. |
| Improve standards in the private rented housing sector | Head of Environmental Health | 25% of 2010/11 private rented inspection programme completed | 40%% of 2010/11 private rented inspection programme completed | 70% of 2010/11 private rented inspection programme completed | 90% of 2010/11 private rented inspection programme completed |
| Significantly improve performance in the delivery of Disabled facilities Grants and Aids and Adaptations and Disabled Facilities Grants | Head of Housing & Head of Environmental Health | Establish baseline performance/customer satisfaction information | TBC subject to RIEP project to review of DFGs and adaptations | TBC subject to RIEP project to review of DFGs and adaptations | TBC subject to RIEP project to review of DFGs and adaptations |
| Complete preparations for retendering of the Older Persons Service (Supporting People) funded services. | Head of Housing | Undertake benchmarking, cost analysis and quality accreditation review of the service | Undertake background documentation preparation, and corporate impact assessment of North West Leicestershire failing to win the tender | Undertake trial submission | Submission of bid. Deadline to be determined by Supporting People |
| Increase the number of additional decent homes in the private sector | Head of Environmental Health | Review and assess the success of 09/10 DHIP project and determine focus for 10/11 | Deliver actions from 10//11 DHIP project. TBC pending outcome of q1 | Deliver actions from 10//11 DHIP project. TBC pending outcome of q1 | Deliver actions from 10//11 DHIP project. TBC pending outcome of q1 |

PRIORITY: GREENFOOT PRINTS

| Action | Lead Officer | Q1 Task | Q2 Task | Q3 Task | Q4 Task |
| --- | --- | --- | --- | --- | --- |
| To establish the Green Footprints Community Network - a district wide network bringing together existing community groups, parish councils, elected members and individuals who are interested in green initiatives. | Head of Place Shaping | Establish the Green Footprints Community Network | Launch the Green Footprints Community Network | Develop a programme of activity for the Green Footprints Community Network | Identify potential funding sources to support the Green Footprints Community Network |
| To prepare and implement a programme of targeted action to increase participation in the Council's recycling collection schemes in areas where recycling performance is poor. | Head of Street Management | To collect data on relative recycling performance of different areas. | To prepare a programme of targeted action in poorly performing areas. | To undertake targeted recycling promotions | To undertake targeted recycling promotions |
| To publicly launch the ‘ourplace’ design initiative and associated strategies | Head of Place Shaping | Formal Public Launch of “our place” | Publish Public Realm Investment Plan | Publish Design Guidance | Prepare shortlist for Design Category of Green Footprints Award |

Section Three: 	Actions and their Tasks

PRIORITY: COALVILLES CHANGING

| Action | Lead Officer | Q1 Task | Q2 Task | Q3 Task | Q4 Task |
| --- | --- | --- | --- | --- | --- |
| To make improvements to Marlborough Square | Coalville’s Changing Programme Manager | Commission a feasibility study to identify potential improvements and funding sources | Develop proposal based on feasibility study and seek Cabinet agreement to progress subject to public consultation | Undertake public consultation on proposed improvements | 1. Cabinet agreement obtained to make improvements. 2. Commence improvement works |
| Use the Council's assets effectively to deliver a more efficient Council and to contribute to Coalville Regeneration | Coalville’s Changing Programme Manager | Review of town centre assets completed | Develop a business case on effective use of town centre assets along with partners | Decision of Cabinet to proceed with preferred option | Implement decision of Cabinet |
| Engage Coalville businesses in setting up a Business Improvement District | Head of Place Shaping | Undertake actions as set out in BID programme | Undertake actions as set out in BID programme | Undertake actions as set out in BID programme | BID ballot held to determine whether a BID will be established in Coalville |
| Support new Town Centre developments | Head of Place Shaping | Work with developers to determine any planning applications for the Town Centre quickly and efficiently | Provide advice and support to developers as required | Provide advice and support to developers as required | Provide advice and support to developers as required |
| Undertake a programme of Town Centre events to attracts visitors and support local businesses | Head of Place Shaping | Hold events for St George’s Day, Coalville Film weekend and Picnic in the Park | Hold Coalville by Sea and Miner’s Gala events | Hold Christmas light switch-on event | Hold programme of events at Coalville Market |

PRIORITY: VALUE FOR MONEY

| Action | Lead Officer | Q1 Task | Q2 Task | Q3 Task | Q4 Task |
| --- | --- | --- | --- | --- | --- |
| To implement Area Working across the District | Head of Place Shaping | Approval of the Area Working Project Plan | Review progress on the area working project plan | Review progress on the area working project plan | Review progress on the area working project plan |
| To improve the availability of performance information to customers and communities | Head of Service Transformation | Establish scope of the information to share and potential communication channels | Implement phase 1 | Review and amend according to customer feedback | Implement phase 2 |
| To undertake targeted cleansing operations to improve the cleanliness of areas scoring poorly in the 4 monthly inspections | Head of Street Management | To identify specific target areas and undertake necessary additional cleaning | To identify specific target areas and undertake necessary additional cleaning | To identify specific target areas and undertake necessary additional cleaning | To identify specific target areas and undertake necessary additional cleaning |
| Deliver procurement savings within the Housing Planned Improvement Savings | Head of Service Transformation | Identify procurement strategy and identify KPI's for sustainable impact measurement | Tender/Access contracts | Meet the requirements of the HPIP programme | Meet the requirements of the HPIP programme |
| Using the category lists to aggregate spend and there by improve value for money through combined spending | Head of Service Transformation | Identify categories | Meet with relevant service managers to identify requirements | Tender or identify frameworks | Identify potential savings and amend supplier list to reflect work |
| Project Management and Support of High Risk Projects | Head of Service Transformation | Deliver actions within the relevant programme and project plans | Deliver actions within the relevant programme and project plans | Deliver actions within the relevant programme and project plans | Deliver actions within the relevant programme and project plans |
| Developing a comprehensive plan to improving the Councils performance against the equalities framework and as such delivering services that meet customers needs | Corporate Director | Agree plan to achieve "achieving level" of the equalities framework | Review EIA plan | Review Equalities Policy/Strategy | Deliver actions in associated plans |

Section Four:	Actions and their Risks

PRIORITY: PRIDE IN OUR COMMUNITY

| Action | Risk | Probability | Impact | Combined Score | Action |
| --- | --- | --- | --- | --- | --- |
| Work with partners to improve levels of public confidence | Home Office focus is diverted to other issues | 1 | 4 | 4 | Proactive PISC Communications Group to promote community safety and give reassurance |
| To make local communities safer by delivering the key objectives in the community Safety Strategy and reducing overall crime by 5% by March 2012 | That the key objectives are not delivered | 2 | 4 | 8 | Ongoing performance management of Strategy action s on a quarterly basis to Strategy Group to highlight areas where actions are failing. |
| To Develop a Planning Strategy for the District | That the Council does not approve the Strategy | 3 | 4 | 12 | Ongoing involvement and discussions with Members throughout process to minimise this risk. |
| Maximise delivery of affordable housing through partnership working | The annual target is not met | 3 | 3 | 9 | Exploring all delivery avenues to mitigate likely reduction of HCA funding and support release of alternative development sites outside River Mease catchment area |
| Implement the outcome of the High Investment Needs Properties Review completed in 2009/10, | Failure to deal with high cost void properties and properties vacant resulting in void loss or unnecessary expenditure | 4 | 3 | 12 | Development of project plan as result of High Investment Needs Properties review with supporting project group to ensure delivery. Ongoing dialogue with customers and key stakeholders |
| Deliver Housing Planned Investment Programme 2010-11 | Housing Planned Investment Programme is not delivered within timescales or within budget | 1 | 3 | 3 | Project managed through project team with representation form key stakeholder groups including tenants and procurement. |
| Increase 16+ Physical Activity uptake | Loss of key physical activity development officers due to being on a fixed term contract. | 2 | 2 | 4 | Regular meetings with the County Sports Partnership to secure funding beyond the fixed term contract. |
| Significantly improve performance in the delivery of Aids and Adaptations for Council tenants | Adaptations requests fail to be processed in a timely manner and customer satisfaction and efficiency are reduced | 2 | 4 | 8 | Continued involvement in the countywide RIEP funded review of DFGs and adaptations to ensure delivery of VFM |
| Complete preparations for retendering of the Older Persons Service (Supporting People) funded services. | Failure to secure the tender for the provision of the older persons service | 3 | 2 | 6 | Undertaking of benchmarking and best practice review; and undertaking of comprehensive mock/trial submission |

PRIORITY: GREEN FOOTPRINTS

| Action | Risk | Probability | Impact | Combined Score | Action |
| --- | --- | --- | --- | --- | --- |
| To publicly launch the ‘ourplace’ design initiative and associated strategies | Commitment to design initiative is lost | 2 | 4 | 8 | Continue to demonstrate the value of design in improving the social desirability, economic performance and environmental sustainability of the district through continued training and ensuring the well designed, approved schemes secure good levels of publicity internally and externally. |
| To establish the Green Footprints Community Network - a district wide network bringing together existing community groups, parish councils, elected members and individuals who are interested in green initiatives. | That the engagement with the 'community' is not successful leaving an unmet need. | 2 | 4 | 8 | Community development programme linked to Area Working |
| To prepare and implement a programme of targeted action to increase participation in the Council's recycling collection schemes in areas where recycling performance is poor. | Lack of public response to the targeted campaigns. | 2 | 3 | 6 | Undertake follow up contact and ongoing monitoring of the impact of the targeted campaigns |

Section Four:	Actions and their Risks

PRIORITY: COALVILLES CHANGING

| Action | Risk | Probability | Impact | Combined Score | Action |
| --- | --- | --- | --- | --- | --- |
| To make improvements to Marlborough Square | Consent to making improvements is not granted by the County Council or the District Council | 2 | 4 | 8 | Work with the County Council to ensure the scheme proposed is acceptable. Incorporate the views of residents on the scheme as part of a consultation following the design stage. |
| Use the Council's assets effectively to deliver a more efficient Council and to contribute to Coalville Regeneration | That the proposed option is not approved | 1 | 4 | 4 | Manage the project carefully through the Coalville’s Changing Programme Board |
| Engage Coalville businesses in setting up a Business Improvement District | That engagement with businesses is unsuccessful | 2 | 4 | 8 | Appoint an independent BID manager who will oversee the process of business engagement up until the BID ballot is held in Q4 |
| Support new Town Centre developments | Determination of the major schemes in Coalville town centre is delayed through a legal challenge or court process | 3 | 4 | 12 | Work with developers, the Government Office for the East Midlands and any other legal or judicial bodies to work through any issues identified as they are raised |
| Undertake a programme of Town Centre events to attracts visitors and support local businesses | Visitors are not attracted to visit the Town Centre by the events programme | 1 | 3 | 3 | Clear communication at an early stage of all events |

PRIORITY: VALUE FOR MONEY

| Action | Risk | Probability | Impact | Combined Score | Action |
| --- | --- | --- | --- | --- | --- |
| To publicly launch the ‘ourplace’ design initiative and associated strategies | Commitment to design initiative is lost | 2 | 4 | 8 | Continue to demonstrate the value of design in improving the social desirability, economic performance and environmental sustainability of the district through continued training and ensuring the well designed, approved schemes secure good levels of publicity internally and externally. |
| To improve the availability of performance information to customers and communities | Available data does not meet customers needs and therefore increases costs of implementation | 2 | 2 | 4 | Consideration of requirements when designing the web page and management of expectations. |
| To implement Area Working across the District | That the Project Plan is not approved | 2 | 4 | 8 | Ongoing engagement with CLT and LSP regarding the development of the project plan. Revisions made as necessary |
| To undertake targeted cleansing operations to improve the cleanliness of areas scoring poorly in the 4 monthly inspections | A high number of target areas may result in a protracted timescale for action | 2 | 2 | 4 | Undertake a review of resources and priority areas for street cleansing actions |
| Deliver procurement savings within the Housing Planned Improvement Savings | The economic climate impact may increase costs and reduce suppliers, thereby reducing the value for money | 2 | 3 | 6 | Monitor the situation and consider the impact when recommendations on future service delivery models. |
| Using the category lists to aggregate spend and there by improve value for money through combined spending | Resistance by services purchasing the goods - will impact on the amount of available spend and reduce saving | 3 | 3 | 9 | Communication with management teams to ensure the necessity of the work and its value is understood. Escalate if co operation is not forthcoming. |
| Project Management and Support of High Risk Projects | Changes in the original agreed scope of each project will impact on capacity, budget and timescales. | 4 | 4 | 16 | Manage expectations if the scope of the project increases and ensure that project plans are updated and the impact of the change taken into consideration. |
| Developing a comprehensive plan to improving the Councils performance against the equalities framework and as such delivering services that meet customers needs | Availability of appropriate expertise | 4 | 4 | 16 | Initially make every effort to retain and utilise the experience that is available to us through the stronger CAT, whilst continuing the development a shared service and looking to market test. |

# Text boxes

Action Plan